## Actions List
Topics | Actions | CIN | DEV | TIN | QUA | PPR | PRD | Resp | Comments
Step 1
Dynamo DB | Creation of new dynamo DBs For storing new ID types in IRL | DONE | DONE | DONE | DONE | DONE | DONE | CCOE
S3 Buckets | Creation of new S3 bucket for storing files linked to the new ID type | DONE | DONE | DONE | DONE | DONE | DONE | CCOE
ASG | Creation of new EC2 instance and ASG for hosting the V3 : | DONE | DONE | DONE | DONE | DONE | DONE | CCOE
Developpment | Remove the ID type from the API Requests | N/A | DONE | DONE | DONE | DONE | DONE | RIDE
Developpment | Reinforcement of the ID | N/A | DONE | DONE | DONE | DONE | DONE | RIDE
Developpment | Generation of ID depending on the Region | N/A | DONE | DONE | DONE | DONE | DONE | RIDE
Developpment | Add the "region" tag in the healthcheck | DONE | DONE | DONE | DONE | DONE | DONE | RIDE
ASG | New Script For user user data. | DONE | DONE | DONE | DONE | DONE | DONE | CCOE
ASG | Creation of new pipelines for Build and Release | DONE | DONE | DONE | DONE | DONE | DONE | RIDE
ASG | deployment of V3 in IRL ASG : | DONE | DONE | DONE | DONE | DONE | DONE | RxDS
Route 53 | Create a specific DNS for the V3 | DONE | DONE | DONE | DONE | DONE | DONE | CCOE
Route 53 | Cname definition (DNS) for each region | N/A | N/A | N/A | DONE | DONE | DONE | CCOE
Route 53 | Set the traffic policies - Latency by default with Automatic Failover if healthcheck is KO thrice in a row - Possibility to force traffic to a specific region | N/A | N/A | N/A | DONE | DONE | DONE | CCOE
ASG | Creation Of EC2 instances and ASGs for Functional API in CANADA | N/A | N/A | N/A | DONE | DONE | DONE | CCOE
RDS Duplication | Create a Replica of RDS (My SQL) for CANADA region | N/A | N/A | N/A | DONE | DONE | DONE | CCOE
Dynamo DB | Configuration of Global Tables for each dynamo DBs | N/A | N/A | N/A | DONE | DONE | DONE | CCOE
S3 Buckets | Creation of S3 buckets in Canada | N/A | N/A | N/A | DONE | DONE | DONE | CCOE
S3 Buckets | Set bidirectionnal replication | N/A | N/A | N/A | DONE | DONE | DONE | CCOE
S3 Buckets | Enable S3 replication from Ireland "deploy" bucket to canada bucket | N/A | N/A | N/A | DONE | DONE | DONE | CCOE
ASG | Deployment of V3 in CANADA ASG | N/A | N/A | N/A | DONE | DONE | DONE | RxDS
Test | Test of V3 with Both region created | N/A | N/A | N/A | DONE | DONE | IN PROGRESS | RxDS
WAF (firewall) | Enable WAF on ALB | DONE | DONE | DONE | DONE | DONE | DONE | CCOE
Step 2
Authentication
Authorization
Monitoring

## Status (hidden)
Status | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
To be started | 48 | 32 | 34 |  |  | 29 | 28 | 18 | 19 | 14 | 13 |  | 11 | 10 | 10 | 0
In progress | 0 | 15 | 15 |  |  | 17 | 19 | 27 | 23 | 27 | 23 |  | 20 | 21 | 20 | 1
Done in PPR | 0 | 0 | 0 |  |  | 3 | 5 | 6 | 6 | 7 | 11 |  | 14 | 14 | 14 | 0
Done in PRD | 0 | 1 | 1 |  |  | 1 | 1 | 3 | 7 | 7 | 8 |  | 10 | 10 | 11 | 0
N/A
Done
Sprint 01. End 11/05-W19
Sprint 02. End 26/05-W21
Sprint 03. End 09/06-W23
Sprint 04. End 23/06-W25