## Slide 1: Monthly Steerco 7 - 16/09/2022
    Infra side:
    CIN/DEV/TIN/QUA/PPR/PRD :
      INFRA in Ireland → DONE.
      INFRA in Canada (only for QUA/PPR/PRD) → DONE
      New DNS for V3 → DONE
      Set the traffic policy (geo-proximity) to be able to route the traffic automatically (only for QUA/PPR/PRD) → DONE
      Change the traffic policy from “geoProximity” to “geoLocation” (only for QUA/PPR/PRD) → DONE
    Application side :
    Creation of dedicated pipelines for Build and Release
    Creation of new user data script
    Remove the ID type from the API Requests
    Reinforcement of the ID
    Generation of ID depending on the Region
    Adding the region info in the healthcheck
Main actions and events
Blocage
Risque
Conforme
The STEP 1(Set the infra replication to canada) is completed. The next action is to start Discussion about current users migration from V1/V2 to V3
The next STEP is the authentication :
First, Change from “actor/application key” to “api key” with api gateway
Then, Set an OAUTH2 mechanism
Questions / Remarks / Risks
eyecloud HAMR - Steerco meeting
Eyecloud HAMR
Implementation – > DONE
Deployment and Test :
  DEV/TIN – RIFT:
    Deployment – > DONE
    Test – > DONE
  QUA (CA and IR) – RIOS:
    Deployment – > DONE
    Test – > DONE
  PPR (CA and IR) – RICS :
    Deployment – > DONE
    Test– > DONE
  PRD (CA and IR) →RICS
    Deployment → DONE
    Test →DONE

## Slide 2: Monthly Steerco 6 - 22/07/2022
    Infra side:
    CIN/DEV/TIN (only in Ireland) → DONE.
    QUA (canada and ireland) → DONE
    PPR (canada and ireland) → DONE
    PRD :
      INFRA in Ireland → DONE.
      INFRA in Canada→ DONE
      New DNS for V3 → DONE
      Set the traffic policy (geo-proximity) to be able to route the traffic automatically → DONE
    Application side :
    Creation of dedicated pipelines for Build and Release
    Creation of new user data script
    Remove the ID type from the API Requests
    Reinforcement of the ID
    Generation of ID depending on the Region
    Adding the region info in the healthcheck
      DEV/TIN → DONE
      QUA → DONE
      PPR → DONE
      PRD → DONE
Main actions and events
Blocage
Risque
Conforme
Today, the traffic policy has been set with GeoProximity → Shall we switch to GeoLocation ?
Questions / Remarks / Risks
eyecloud HAMR - Steerco meeting
Eyecloud HAMR
Implementation – > DONE
Deployment and Test :
  DEV/TIN – RIFT:
    Deployment – > DONE
    Test – > DONE
  QUA (CA and IR) – RIOS:
    Deployment – > DONE
    Test – > DONE
  PPR (CA and IR) – RICS :
    Deployment – > DONE
    Test– > DONE
  PRD CA and IR) →RICS
    Deployment → DONE
    Test → In Progress

## Slide 3: Monthly Steerco 5 - 28/06/2022
    Infra side:
    CIN/DEV/TIN (only in Ireland) → DONE.
    QUA (canada and ireland) → DONE
    PPR
      INFRA in Ireland → DONE.
      INFRA in Canada→ DONE
      New DNS for V3 → DONE
      Set the traffic policy (geo-proximity) to be able to route the traffic automatically → Set by CCOE (test in progress)
    PRD : Tasks about infrastructure creation will be added in the CCOE’s backlog once validation on PPR will be done (expected this week)
    Application side :
    Creation of dedicated pipelines for Build and Release
    Creation of new user data script
    Remove the ID type from the API Requests
    Reinforcement of the ID
    Generation of ID depending on the Region
    Adding the region info in the healthcheck
      DEV/TIN → DONE
      QUA → DONE
      PPR → TO be deployed
Main actions and events
Blocage
Risque
Conforme
Questions / Remarks / Risks
eyecloud HAMR - Steerco meeting
Eyecloud HAMR
Implementation – > DONE
Deployment and Test :
  DEV/TIN – RIFT:
    Deployment – > DONE
    Test – > DONE
  QUA (CA and IR) – RIOS:
    Deployment – > DONE
    Test – > DONE
  PPR (CA and IR) – RICS :
    Deployment – > DONE
    Test– > DONE

## Slide 4: Monthly Steerco 4 - 20/05/2022
    Infra side:
    CIN/DEV/TIN (only in Ireland) → DONE.
    QUA (canada and ireland) → DONE
    PPR
      INFRA in Ireland → DONE.
      INFRA in Canada→ DONE
      Set the traffic policy to be able to route the traffic automatically → IN PROGRESS
    Application side :
    Creation of dedicated pipelines for Build and Release
    Creation of new user data script
    Remove the ID type from the API Requests
    Reinforcement of the ID
    Generation of ID depending on the Region
Main actions and events
Blocage
Risque
Conforme
STEP 1 :
Traffic Policy activation is on hold in PPR :
  We had to change the DNS for the V3. The Goal is to apply a specific DNS for the new V3 in order to avoid impacting the V1/V2 version with the new traffic policy. → DNS have been created on CIN/DEV/TIN and test are scheduled for next week.
  Due to the issue faced in GDP with US and CANADA users with latency, we will probably switch from “Latency” to “Geoproximity” (or geolocation) route policy
Questions / Remarks / Risks
eyecloud HAMR - Steerco meeting
Eyecloud HAMR
Implementation – > DONE
Deployment and Test :
  DEV/TIN – RIFT:
    Deployment – > DONE
    Test – > DONE
  QUA (CA and IR) – RIOS:
    Deployment – > DONE
    Test – > DONE
  PPR (CA and IR) – RICS :
    Deployment – > DONE
    Test – > TO DO

## Slide 5: Monthly Steerco 3 - 15/04/2022
    Infra side:
    CIN/DEV/TIN (only in Ireland) → DONE.
    QUA
      Ireland → DONE.
      Canada→ IN PROGRESS
        Creation of bucket in canada region to store the files → DONE.
        Set bi directional replication between ireland and canada buckets → DONE.
        Set the global table feature in order to have dynamoDB in both Region → DONE.
        Create a Replica of RDS (Mysql) for CANADA region → DONE.
        Creation of new ASG in canada for eyecloud V3 → DONE.
        Creation of a bucket to host package in canada → DONE.
        Set the traffic policy to be able to route the traffic → IN PROGRESS
    Application side :
    Creation of dedicated pipelines for Build and Release
    Creation of new user data script
    Remove the ID type from the API Requests
    Reinforcement of the ID
    Generation of ID depending on the Region
Main actions and events
Blocage
Risque
Conforme
STEP 1 :
Traffic Policy setting is in progress : Souad is waiting the support of AWS in order to increase the quotas of records within traffic policy
Next step is setting the infra on PPR
STEP 2 :
Rashmi will leave the company on20th of April. She has been the developer of eyecloud and authz
Questions / Remarks / Risks
eyecloud HAMR - Steerco meeting
Eyecloud HAMR
Implementation – > DONE
Deployment and Test :
  DEV/TIN :
    Deployment – > DONE
    Test – > DONE
  QUA (CA and IR) :
  Deployment – > DONE
  Test – > DONE

## Slide 6
HAMR API Traffic Policy with Route53 on AWS

## Slide 7: Monthly Steerco 2 - 18/03/2022
    Infra side:
    CIN/DEV/TIN (only in Ireland) → DONE.
    QUA
      Ireland → DONE.
      Canada→ TO DO (tasks have been added in the CCOE backlog) :
        Creation of bucket in canada region to store the files
        Set bi directional replication between ireland and canada buckets
        Set the Route 53 to be able to route the traffic (metrics have to be defined)
        Set the global table feature in order to have dynamo DB in both Region
        Creation of new ASG in canada for eyecloud V3
        Creation of a bucket to host package in canada
    Application side :
    Creation of dedicated pipelines for Build and Release
    Creation of new user data script
    Remove the ID type from the API Requests
    Reinforcement of the ID
    Generation of ID depending on the Region
Main actions and events
Blocage
Risque
Conforme
STEP 1 :
The infra has to be set up in QUA canada.
STEP 2 :
“Analysis” user stories have been created in the current sprint, in order to identify the change that we have to do in application side :
  For the authentication part : change from “actor_key/application_key” to “Api_key” with Api gateway.
  For Authorization part : migration to Authz
Rashmi will leave the company on end of March. who has been the developer of eyecloud and authz
Questions / Remarks / Risks
eyecloud HAMR - Steerco meeting
Eyecloud HAMR
Implementation – > DONE
Deployment and Test :
  DEV/TIN :
    Deployment – > DONE
    Test – > DONE
  QUA IR :
  Deployment – > DONE
  Test → IN PROGRESS

## Slide 8: Monthly Steerco 1 - 18/02/2022
    Infra AWS :
Dynamo DBs and Buckets :
    CIN / DEV → DONE.
    Next step, Set infra in TIN (Ticket has been added in the CCOE backlog)
    APPlication :
Implementation of the V3 :
Current sprint
    Creation of dedicated pipelines for Build and Release →DONE
    Creation of new user data script → IN PROGRESS
    Remove the ID type from the API Requests → TO DO
Next Sprint
    Reinforcement of the ID
    Generation of ID depending on the Region
Main actions and events
Blocage
Risque
Conforme
STEP 1 :
The infra has to be set up in TIN for the test purpose (from RIFT team) → CCOE’s members are fully busy working massively on GDP migration. They won’t be available next week for this task. We will validate the implementation on dev env for now.
STEP 2 :
For the authentication part : we will align with what will be done on GDP topic. So probably:
  First, Set the “api key” process
  Then, set the Oauth2 with a dedicated ID provider
Rashmi will leave the company on end of March. who has been the developer of eyecloud and authz
Questions / Remarks / Risks
eyecloud HAMR - Steerco meeting
Eyecloud HAMR

## Slide 9: RoadMap
2021 | 2022
November | December | Q1 | Q2 | Q3 | Q4
Scoping / Requirements
Scoping STEP
Route 53
Conception and Realization STEP 1
S3 Replication
Global table in Dynamo DBs
I
0
Discussion with users
Realization
Id uniqueness enhancement
ASGs duplication
Authentication
Authorization
Conception and Realization STEP 2